## Production
Calander week | Date | Budgeted resources | No. of resources worked | Actual weekly target as per budgeted resources | Actual weekly target as per worked resources | Achieved weekly target | Differece | Status | Remarks
CW14 | 04-04-2022 to 08-04-2022 | 0 | 0 | 235 | 0 | 0 | 0 | 0 | 0
CW15 | 11-04-2022 to 15-04-2022 | 0 | 0 | 235 | 0 | 0 | 0 | 0 | 0
CW16 | 18-04-2022 to 22-04-2022 | 0 | 0 | 235 | 0 | 0 | 0 | 0 | 0
CW17 | 25-04-2022 to 29-04-2022 | 0 | 0 | 235 | 0 | 0 | 0 | 0 | 0
CW18 | 02-05-2022 to 06-05-2022 | 0 | 0 | 235 | 0 | 0 | 0 | 0 | 0
CW19 | 09-05-2022 to 13-05-2022 | 0 | 0 | 235 | 0 | 0 | 0 | 0 | 0
CW20 | 16-05-2022 to 20-05-2022 | 0 | 0 | 235 | 0 | 0 | 0 | 0 | 0
CW21 | 23-05-2022 to 27-05-2022 | 0 | 0 | 235 | 0 | 0 | 0 | 0 | 0
CW22 | 30-05-2022 to 03-06-2022 | 0 | 0 | 235 | 0 | 0 | 0 | 0 | 0
CW23 | 06-06-2022 to 10-06-2022 | 0 | 0 | 235 | 0 | 0 | 0 | 0 | 0
CW24 | 13-06-2022 to 17-06-2022 | 0 | 0 | 235 | 0 | 0 | 0 | 0 | 0
CW25 | 20-06-2022 to 24-06-2022 | 0 | 0 | 235 | 0 | 0 | 0 | 0 | 0
CW26 | 27-06-2022 to 01-07-2022 | 0 | 0 | 235 | 0 | 0 | 0 | 0 | 0
CW27 | 04-07-2022 to 08-07-2022 | 0 | 0 | 235 | 0 | 0 | 0 | 0 | 0
CW28 | 11-07-2022 to 15-07-2022 | 0 | 0 | 235 | 0 | 0 | 0 | 0 | 0
CW29 | 18-07-2022 to 22-07-2022 | 0 | 0 | 235 | 0 | 0 | 0 | 0 | 0
CW30 | 25-07-2022 to 29-07-2022 | 0 | 0 | 235 | 0 | 0 | 0 | 0 | 0
CW31 | 01-08-2022 to 05-08-2022 | 0 | 0 | 235 | 0 | 0 | 0 | 0 | 0
CW32 | 08-08-2022 to 12-08-2022 | 0 | 0 | 235 | 0 | 0 | 0 | 0 | 0
CW33 | 15-08-2022 to 19-08-2022 | 0 | 0 | 235 | 0 | 0 | 0 | 0 | 0
CW34 | 22-08-2022 to 26-08-2022 | 0 | 0 | 235 | 0 | 0 | 0 | 0 | 0
CW35 | 29-08-2022 to 02-09-2022 | 0 | 0 | 235 | 0 | 0 | 0 | 0 | 0
CW36 | 05-09-2022 to 09-09-2022 | 0 | 0 | 235 | 0 | 0 | 0 | 0 | 0
CW37 | 12-09-2022 to 16-09-2022 | 0 | 0 | 235 | 0 | 0 | 0 | 0 | 0
CW38 | 19-09-2022 to 23-09-2022 | 0 | 0 | 235 | 0 | 0 | 0 | 0 | 0
CW39 | 26-09-2022 to 30-09-2022 | 0 | 0 | 235 | 0 | 0 | 0 | 0 | 0
CW40 | 03-10-2022 to 07-10-2022 | 0 | 0 | 235 | 0 | 0 | 0 | 0 | 0
CW41 | 10-10-2022 to 14-10-2022 | 0 | 0 | 235 | 0 | 0 | 0 | 0 | 0
CW42 | 17-10-2022 to 21-10-2022 | 0 | 0 | 235 | 0 | 0 | 0 | 0 | 0
CW43 | 24-10-2022 to 28-10-2022 | 0 | 0 | 235 | 0 | 0 | 0 | 0 | 0
CW44 | 31.Oct - 04.Nov | 11 | 5.83 | 235 | 129 | 200 | -71 | On track | 1. Nilesh, Pawan, Mahesh, Disha were on diwali vacation. 2. Sunaina was on sick leave (3 days). 3. Hari Krishna was on personal leave (2 days). | 1096
CW45 | 07.Nov - 11.Nov | 11 | 8.33 | 235 | 228 | 208 | 20 | Moderate | 1. Hari Krishna, Aslam, Kaleem, Rahul spent time on rework due to lot of mistakes.
CW46 | 14.Nov - 18.Nov | 11 | 6.8 | 235 | 162 | 123 | 39 | High risk | 1. Mahesh was on leave (1day). 2. Nilesh is on emergency leave. 3.Aslam is on emergency leave (2days)
CW47 | 21.Nov - 25.Nov | 11 | 8 | 235 | 260 | 183 | 77 | High risk | 1. Nilesh is on emergency leave. 2.Gaurav is on leave (21/11/2022). 3.Aslam on leave (21/11/2022). 4.Rahul on sick leave (21/11/2022). 5.Sunaina on sick leave(24/11/2022). 6.Aslam,Kaleem,Rahul,Hari krishna this guys done only incorporation (23/11/2022). 7.Pawan on leave (25/11/2022).
CW48 | 28.Nov - 02.Dec | 11 | 11 | 235 | 317 | 257 | 60 | High risk | 1.Nilesh is on leave (28/11/2022). 2.Disha is on leave (30/11/2022). 3.Town hall meeting from 10.50 AM - 12.35 PM on (11/29/2022). 4.Nilesh,Mahesh,Sunaina,Pawan,Disha,Shesadri worked in grid & references on 12/2/2022
CW49 | 05.Dec - 09.Dec | 11 | 6.2 | 235 | 147 | 128 | 19 | High risk | 1. Total team worked for VD143 Grid & Reference (07/12/2022 to 08/12/2022) 2.Rahul is on leave(5/12/2022 to 7/12/2022) 3. Mahesh is on Leave (6/12/2022 to 9/12/2022) 4.Gourav is on leave(09/12/2022) 5.Pawan Worked in SD300 Series
CW50 | 12.Dec - 16.Dec | 11 | 10.6 | 235 | 170 | 147 | 23 | High risk | 1.Total team rechecked VD143 (12/12/2022 2.Sunaina is on leave(12/12/2022) 3.Disha is on leave (13/12/2022) 4.Sheshadri is on leave(12/12/2022 to 14/12/2022) 5. 1Hr HR meeting conducted(16/12/2022)
CW51 | 19.Dec - 23.Dec | 11 | 10.2 | 235 | 178 | 176 | 2 | Moderate | 1.Total Team Checked G&R VD147 2Days (20/12/2022 & 23/12/2022) 2.Kaleem is on leave 4days(19/12/2022 to 22/12/2022) 3.Pawan Working in SD300 Series.
CW52 | 26.Dec - 30.Dec | 11 | 5.8 | 235 | 106 | 109 | -3 | On track | 1.Total team worked for new updates incorporation and grid and reference(28/12/2022 to 30/12/2022) 2.Sheshadri is on leave (26/12/2022 to 28/12/2022) 3.Disha is on sick leave(28/12/2022) 4.Pawan is working on SD300 Series 5.Mahesh is worked in SD500 Series(26/12/2022)
CW01 | 02.Jan - 06.Jan | 10 | 5.4 | 235 | 108 | 112 | -4 | On track | 1.Almost all team worked for new updates and grid and reference(02/01/2023 to 06/01/2023). 2.Pawan & Mahesh is working in SD300 Series.
CW02 | 09-Jan - 13-Jan | 10 | 5 | 235 | 74 | 73 | 1 | Moderate | 1. Team is forked for New updates, Grid & Ref and QC With incorporation of different projects. 2.Pawan and Mahesh is working in SD300 Series.
CW03 | 16-Jan - 20-Jan | 10 | 7 | 235 | 149 | 139 | 10 | High risk | 1.Gaurav is on leave for a week. 2.Team is worked for new updates,Grid & ref and Quality 3.Disha is on sick leave 4.Hari,Siyam&Aslam is on leave.
CW04 | 23-Jan - 27-Jan | 10 | 8.5 | 235 | 141 | 143 | -2 | On track | 1.Gaurav is on leave for a week. 2.pawan dhok on sick leave for half day.(24-01-2023) 3.Holiday:REPUBLIC DAY
CW05 | 30-Jan - 03-Feb | 10 | 9 | 235 | 214 | 198 | 16 | High risk | 1.Kaleem is on sick leave from monday 2nd half. 2.pawan worked for SD309 on 01-02-2023, 3.almost half day internet issue on 02-02-2023
CW06 | 06-Feb - 11-Feb | 10 | 7.8333 | 235 | 234 | 241 | -7 | On track | 1.Disha is on leave 2.Sunaina is on leave(9 & 10-feb) 3.Nilesh,Sunaina,Pavan worked for Grid&Ref 4.Kaleem is on leave(6&7-Feb)
CW07 |  | 10 | 8 | 235 | 300 | 315 | -15 | On track | 0
CW08 |  | 10 | 0 | 235 | 0 | 0 | 0 | 0 | 0
CW09 |  | 0 | 0 | 235 | 0 | 0 | 0 | 0 | 0
CW10 |  | 0 | 0 | 235 | 0 | 0 | 0 | 0 | 0
CW11 |  | 0 | 0 | 235 | 0 | 0 | 0 | 0 | 0
CW12 |  | 0 | 0 | 235 | 0 | 0 | 0 | 0 | 0
CW13 |  | 0 | 0 | 235 | 0 | 0 | 0 | 0 | 0

## Quality
Calander week | Date | Budgeted resources |  | No. of resources worked |  | Actual weekly target as per budgeted resources |  | Actual weekly target as per worked resources |  | Achieved weekly target |  | Quality percentage |  | Differece |  | Status | Remarks
|  | QC-1 | QC-2 | QC-1 | QC-2 | QC-1 | QC-2 | QC-1 | QC-2 | QC-1 | QC-2 | QC-1 | QC-2 | QC-1 | QC-2
CW45 | 31.Oct - 04.Nov | 2 | 2 | 2 | 1 | 200 | 200 | 100 | 50 | 112 | 54 | 94% | - | -12 | -4 | Moderate | 1. Vaibhav was on diwali vacation. 2. VD141 is a difficult project and due to project difficulty reduced the daily targets.
CW46 | 07.Nov - 11.Nov | 2 | 2 | 4 | 2 | 200 | 200 | 360 | 110 | 311 | 116 | 94% | - | 49 | -6 | High risk | 1. To close the gap added 3 more resources in QC-1.
CW47 | 14.Nov - 18.Nov | 2 | 2 | 4.8333 | 2 | 200 | 200 | 393 | 155 | 344 | 150 | 95% | - | 49 | 5 | Moderate | 1. To close the gap added 3 more resources in QC-1. 2. Reworking on VD141 due to too many errors.
CW48 | 21.Nov - 25.Nov | 2 | 2 | 2.666 | 2 | 200 | 200 | 320 | 190 | 229 | 157 | 96% |  | 91 | 33 | High risk | 1.Vaibhav was worked in VD141 on 11/21/2022, so target reduced to 10. 2. Siyam and Sheshadri prepared query sheet for VD147 on 11/22/2022. 3. To close the gap added 1 more resources in QC-1.
CW49 | 28.Nov - 02.Dec | 2 | 2 | 2.4 | 2 | 200 | 200 | 181 | 100 | 173 | 95 | 96% |  | 8 | 5 | Moderate | 1. Vaibhav was on half day leave due to sick on 11/28/2022. 2. Town hall meeting from 10.50 AM - 12.35 PM on 11/29/2022. 3.Seshadri worked in QC1 from 11/28/2022 to 11/30/2022 4.Siyam and Vaibhav worked in Recheck and updation for VD143 from 12/1/2022 -12/2/2022
CW50 | 05.Dec - 09.Dec | 2 | 2 | 1.8 | 2 | 200 | 200 | 169 | 160 | 169 | 160 | 97% |  | 0 | 0 | On track | 1. From 12/6/2022 - 12/9/2022 QC-2 target reduced to 15 as per request to recheck of VD143 files. 2.For recheck of VD143, QC-1 target reduced to 15 on 12/9/2022 due to mistakes found by QC-3. 3. Divyanand was on leave due to sick on 12/9/2022.
CW51 | 12.Dec - 16.Dec | 2 | 2 | 2 | 2 | 200 | 200 | 121 | 68 | 115 | 56 | 97% |  | 6 | 12 | Moderate | 1. From 12/12/2022 - 12/14/2022 QC-2 did recheck of VD143 files(Doc B & c). 2.For recheck of VD143, QC-1 did recheck of VD143 on 12/12/2022. 3.On 12/15/2022 QC-1 target reduced to 7 because of complexity(VD145) 4.Vaibhav was on half day leave due to sick on 12/16/2022. 5. On 12/16/2022 HR meeting from 2.00pm to 3.00 pm
CW52 | 19.Dec - 23.Dec | 2 | 2 | 2 | 2 | 200 | 200 | 115 | 200 | 115 | 196 | 97% |  | 0 | 4 | Moderate | 1. VD145 & VD149 is a difficult project and due to project difficulty reduced the daily targets for QC1 as12. 2.Sohan's Target reduced to 10 beacause of SD309(QC1)
CW53 | 26.Dec - 30.Dec | 2 | 2 | 2 | 2 | 200 | 200 | 120 | 200 | 117 | 190 | 97% |  | 3 | 10 | Moderate | 1. VD145 & VD149 is a difficult project and due to project difficulty reduced the daily targets for QC1 as12.
CW01 | 2.Jan-6.Jan | 2 | 2 | 2 | 2 | 200 | 200 | 120 | 180 | 128 | 179 | 97% |  | -8 | 1 | On track
CW02 | 09.Jan - 13.Jan | 2 | 2 | 2 | 2.2 | 200 | 200 | 102 | 165 | 102 | 167 | 97% |  | 0 | -2 | On track | 1. VD145 & VD149 is a difficult project and due to project difficulty reduced the daily targets for QC1 as12. 2.Sohan's Target reduced to 10 beacause of SD309(QC1)
CW03 | 16.Jan - 20.Jan | 2 | 2 | 2 | 1 | 200 | 200 | 137 | 80 | 119 | 80 | 97% |  | 18 | 0 | Moderate | 1. VD145 & VD149 is a difficult project and due to project difficulty reduced the daily targets for QC1 as12. 2.Sohan's Target reduced to 6 beacause of SD309(QC1) 3.Siyam(QC-2) was on leave for the complete week.
CW04 | 23.Jan - 27.Jan | 1 | 2 | 1 | 2 | 200 | 200 | 80 | 160 | 80 | 160 | 97% |  | 0 | 0 | On track | 1. Sohan (QC-1) was on vacation.
CW05 | 30.Jan - 3.Feb | 2 | 2 | 2 | 2 | 200 | 200 | 183 | 200 | 183 | 200 | 97% |  | 0 | 0 | On track | 1.Sohan's Target reduced beacause of SD309(QC1)
CW06 | 6 Feb-11 Feb | 2 | 2 | 2 | 2 | 200 | 200 | 80 | 200 | 80 | 203 | 97% |  | 0 | -3 | On track | 1.From 2/8/2023 - 2/11/2023 Sohan & Divyanand worked in production 2.On 2/10/2023 & 2/11/2023 Sohan was on leave.
CW07 | 13 Feb-17 Feb | 2 | 2 | 1.67 | 2 | 200 | 200 | 100 | 200 | 98 | 168 | 97% |  | 2 | 32 | Moderate | 1.From 2/13/2023, 2/11/2023 &2/17/2023 Divyanand worked in production 2.On 2/13/2023 & 2/14/2023 Sohan was on leave.
[6 empty] | 2600 | 2600 | 2318 | 1818 | 2114 | 1760 |  |  | 204 | 58

## Resource allocation
Resource | Activity | Task
Siyam | QC-2
Vaibhav | QC-2
Divyanad | QC-1
Sohan | QC-1
Pawan | Production |  | 6
Disha | Production |  | 6
Sunaina | Production |  | 6
Nilesh | Production |  | 6
Mahesh | Production |  | 6
Gaurav | Production |  | 6
Kaleem | Production |  | 4
Aslam | Production |  | 4
Harikrishna | Production |  | 4
Rahul | Production |  | 4

## Definition
On track | >= allocated target
Moderate | >= (allocated target-20)
Risk | <= (allocated target-30)
High risk | <= (allocated target-40)

## Production weekly data
Week |  | No. of resources | Target | Achieved
CW44 | 2022-10-31 | 7 | 30 | 45
| 2022-11-01 | 7 | 30 | 33
| 2022-11-02 | 6 | 25 | 30
| 2022-11-03 | 5 | 22 | 25
| 2022-11-04 | 5 | 22 | 29
| 2022-11-05 | 5 |  | 38
|  | 5.8333 | 129 | 200
CW45 | 2022-11-07 | 10 | 56 | 38
| 2022-11-08 | 8 | 52 | 53
| 2022-11-09 | 8 | 44 | 40
| 2022-11-10 | 8 | 32 | 27
| 2022-11-11 | 8 | 44 | 29
| 2022-11-12 | 8 |  | 21
|  | 8.3333 | 228 | 208
CW46 | 2022-11-14 | 6 | 28 | 17
| 2022-11-15 | 7 | 34 | 23
| 2022-11-16 | 7 | 36 | 21
| 2022-11-17 | 6 | 32 | 24
| 2022-11-18 | 6 | 32 | 22
| 2022-11-19 | 5 |  | 16
|  | 6.4 | 162 | 123
CW47 | 2022-11-21 | 6 | 34 | 29
| 2022-11-22 | 9 | 48 | 42
| 2022-11-23 | 9 | 65 | 21
| 2022-11-24 | 8 | 55 | 34
| 2022-11-25 | 8 | 58 | 32
| 2022-11-26 | 8 |  | 25
|  | 8 | 260 | 183
CW48 | 2022-11-28 | 9 | 56 | 52
| 2022-11-29 | 11 | 59 | 55
| 2022-11-30 | 10 | 78 | 70
| 2022-12-01 | 11 | 62 | 58
| 2022-12-02 | 11 | 62 | 22
|  | 10.4 | 317 | 257
CW49 | 2022-12-05 | 10 | 58 | 49 | Name | Actual Target | Achieved Target | Balance
| 2022-12-06 | 9 | 35 | 27 | Gaurav | 10 | 7 | 3
| 2022-12-07 | 1 | 3 | 3 | Nilesh | 15 | 16 | -1
| 2022-12-08 | 2 | 7 | 6 | Mahesh | 6 | 4 | 2
| 2022-12-09 | 9 | 44 | 43 | Sunaina | 15 | 16 | -1
Total |  | 6.2 | 147 | 128 | ASLAM | 15 | 9 | 6
[5 empty] | RAHUL | 10 | 10 | 0
[5 empty] | KALEEM | 15 | 11 | 4
[5 empty] | HARI | 15 | 13 | 2
[5 empty] | DISHA | 15 | 15 | 0
[5 empty] | PAWAN DHOK | 18 | 17 | 1
[5 empty] | SHESHADRI | 13 | 10 | 3
[5 empty] | Total | 147 | 128 | 19
CW50 | 2022-12-12 | 0 | 0 | 0 | Name | Actual Target | Achieved Target | Balance
| 2022-12-13 | 9 | 29 | 28 | Gaurav | 16 | 14 | 2 | Saturday
| 2022-12-14 | 14 | 41 | 37 | Nilesh | 16 | 16 | 0
| 2022-12-15 | 15 | 50 | 42 | Mahesh | 10 | 9 | 1
| 2022-12-16 | 15 | 50 | 40 | Sunaina | 16 | 15 | 1 | Saturday
Total |  | 10.6 | 168 | 147 | ASLAM | 12 | 11 | 1
[5 empty] | RAHUL | 12 | 13 | -1
[5 empty] | KALEEM | 12 | 12 | 0
[5 empty] | HARI | 12 | 12 | 0
[5 empty] | DISHA | 12 | 12 | 0
[5 empty] | PAWAN DHOK | 10 | 9 | 1
[5 empty] | SHESHADRI | 8 | 7 | 1
[5 empty] | Swetha | 8 | 4 | 4
[5 empty] | Yogesh | 8 | 6 | 2
[5 empty] | Kartik | 8 | 2 | 6
[5 empty] | Laxman | 8 | 5 | 3
[5 empty] | Total | 168 | 147 | 21
CW50 | 2022-12-19 | 10 | 34 | 30 | Name | Actual Target | Achieved Target | Balance
| 2022-12-20 | 10 | 30 | 31 | Gaurav | 18 | 18 | 0
| 2022-12-21 | 10 | 40 | 38 | Nilesh | 18 | 18 | 0
| 2022-12-22 | 10 | 40 | 42 | Mahesh | 32 | 29 | 3
| 2022-12-23 | 11 | 34 | 35 | Sunaina | 18 | 18 | 0
Total |  | 10.2 | 178 | 176 | ASLAM | 14 | 14 | 0
[5 empty] | RAHUL | 13 | 13 | 0
[5 empty] | KALEEM | 2 | 2 | 0
[5 empty] | HARI | 13 | 13 | 0
[5 empty] | DISHA | 18 | 18 | 0
[5 empty] | PAWAN DHOK | 13 | 14 | -1
[5 empty] | SHESHADRI | 19 | 19 | 0
[5 empty] | Total | 178 | 176 | 2
CW51 | 2022-12-26 | 10 | 37 | 35 | Name | Actual Target | Achieved Target | Balance
| 2022-12-27 | 10 | 31 | 28 | Gaurav | 13 | 14 | -1
| 2022-12-28 | 6 | 30 | 36 | Nilesh | 6 | 5 | 1
| 2022-12-29 | 2 | 7 | 7 | Mahesh | 12 | 10 | 2
| 2022-12-30 | 1 | 3 | 3 | Sunaina | 6 | 6 | 0
Total |  | 5.8 | 108 | 109 | ASLAM | 11 | 15 | -4
[5 empty] | RAHUL | 12 | 12 | 0
[5 empty] | KALEEM | 12 | 12 | 0
[5 empty] | HARI | 11 | 11 | 0
[5 empty] | DISHA | 6 | 6 | 0
[5 empty] | PAWAN DHOK | 15 | 13 | 2
[5 empty] | SHESHADRI | 4 | 5 | -1
[5 empty] | Total | 108 | 109 | -1
CW01 | 2023-01-02 | 7 | 23 | 26 | Name | Actual Target | Achieved Target | Balance
| 2023-01-03 | 8 | 23 | 28 | Gaurav | 2 | 2 | 0
| 2023-01-04 | 3 | 10 | 7 | Nilesh | 0 | 1 | -1
| 2023-01-05 | 6 | 43 | 42 | Mahesh | 13 | 9 | 4
| 2023-01-06 | 3 | 9 | 9 | Sunaina | 12 | 12 | 0
Total |  | 5.4 | 108 | 112 | ASLAM | 6 | 7 | -1
[5 empty] | RAHUL | 7 | 12 | -5
[5 empty] | KALEEM | 7 | 8 | -1
[5 empty] | HARI | 3 | 5 | -2
[5 empty] | DISHA | 3 | 3 | 0
[5 empty] | PAWAN DHOK | 15 | 14 | 1
[5 empty] | Swetha | 9 | 9 | 0
[5 empty] | Yogesh | 9 | 9 | 0
[5 empty] | Laxman | 12 | 12 | 0
[5 empty] | Kartik | 10 | 9 | 1
[5 empty] | Total | 108 | 112 | -4
CW02 | 2023-01-09 | 10 | 34 | 30 | Name | Actual Target | Achieved Target | Balance
| 2023-01-10 | 8 | 20 | 19 | Gaurav | 6 | 6 | 0
| 2023-01-11 | 3 | 9 | 9 | Nilesh | 6 | 4 | 2
| 2023-01-12 | 3 | 8 | 10 | Mahesh | 12 | 7 | 5
| 2023-01-13 | 1 | 3 | 5 | Sunaina | 6 | 6 | 0
Total |  | 5 | 74 | 73 | ASLAM | 10 | 10 | 0
[5 empty] | RAHUL | 3 | 5 | -2
[5 empty] | KALEEM | 3 | 5 | -2
[5 empty] | HARI | 6 | 6 | 0
[5 empty] | DISHA | 7 | 7 | 0
[5 empty] | PAWAN DHOK | 15 | 17 | -2
[5 empty] | Total | 74 | 73 | 1
CW03 | 2023-01-16 | 1 | 9 | 6 | Name | Actual Target | Achieved Target | Balance
| 2023-01-17 | 6 | 27 | 23 | Gaurav | 0 | 0 | 0
| 2023-01-18 | 8 | 34 | 30 | Nilesh | 13 | 14 | -1
| 2023-01-19 | 9 | 39 | 41 | Mahesh | 45 | 33 | 12
| 2023-01-20 | 11 | 40 | 39 | Sunaina | 13 | 13 | 0
Total |  | 7 | 149 | 139 | ASLAM | 12 | 13 | -1
[5 empty] | RAHUL | 16 | 16 | 0
[5 empty] | KALEEM | 16 | 16 | 0
[5 empty] | HARI | 12 | 12 | 0
[5 empty] | DISHA | 11 | 11 | 0
[5 empty] | PAWAN DHOK | 8 | 8 | 0
[5 empty] | YOGESH | 1 | 1 | 0
[5 empty] | Laxman | 1 | 1 | 0
[5 empty] | Swetha | 1 | 1 | 0
[5 empty] | Total | 149 | 139 | 10
CW04 | 2023-01-23 | 9 | 41 | 40 | Name | Actual Target | Achieved Target | Balance
| 2023-01-24 | 8 | 32 | 31 | Gaurav | 0 | 0 | 0
| 2023-01-25 | 8 | 32 | 32 | Nilesh | 16 | 16 | 0
| 2023-01-26 | Holiday |  |  | Mahesh | 13 | 13 | 0
| 2023-01-27 | 9 | 36 | 40 | Sunaina | 16 | 16 | 0
Total |  | 8.5 | 141 | 143 | ASLAM | 16 | 16 | 0
[5 empty] | RAHUL | 16 | 16 | 0
[5 empty] | KALEEM | 16 | 16 | 0
[5 empty] | HARI | 16 | 16 | 0
[5 empty] | DISHA | 16 | 16 | 0
[5 empty] | PAWAN DHOK | 16 | 18 | -2
[5 empty] | Total | 141 | 143 | -2
CW05 | 2023-01-30 | 10 | 45 | 45 | Name | Actual Target | Achieved Target | Balance
| 2023-01-31 | 9 | 41 | 40 | Gaurav | 23 | 19 | 4
| 2023-02-01 | 8 | 38 | 40 | Nilesh | 23 | 21 | 2
| 2023-02-02 | 9 | 45 | 31 | Mahesh | 31 | 25 | 6
| 2023-02-03 | 9 | 45 | 42 | Sunaina | 23 | 22 | 1
Total |  | 9 | 214 | 198 | ASLAM | 23 | 22 | 1
[5 empty] | RAHUL | 23 | 22 | 1
[5 empty] | KALEEM | 4 | 3 | 1
[5 empty] | HARI | 23 | 21 | 2
[5 empty] | DISHA | 23 | 23 | 0
[5 empty] | PAWAN DHOK | 18 | 20 | -2
[5 empty] | Total | 214 | 198 | 16
CW06 | 2023-06-02 | 8 | 40 | 41 | Name | Actual Target | Achieved Target | Balance | Remarks
| 2023-07-02 | 8 | 39 | 44 | Gaurav | 30 | 28 | 2 | Last week still 2 File balance
| 2023-08-02 | 8 | 40 | 51 | Nilesh | 14 | 14 | 0
| 2023-09-02 | 8 | 40 | 37 | Mahesh | 25 | 22 | 3 | Last week 4 files balance
| 2023-10-02 | 9 | 45 | 43 | Sunaina | 10 | 10 | 0
| 2023-11-02 | 6 | 30 | 25 | ASLAM | 30 | 30 | 0
Total |  | 7.8333 | 234 | 241 | RAHUL | 30 | 29 | 1
[5 empty] | KALEEM | 20 | 19 | 1
[5 empty] | HARI | 30 | 30 | 0
[5 empty] | PAWAN DHOK | 15 | 18 | -3
[5 empty] | SOHAN | 10 | 17 | -7
[5 empty] | DIVYANAND | 20 | 24 | -4
[5 empty] | Total | 234 | 241 | -7

## Quality weekly data
Week | Date | QC1 |  |  | QC2
|  | No. of resources | Target | Achieved | No. of resources | Target | Achieved
CW44 | 2022-10-31 | 2 | 20 | 16 | 1 | 10 | 11
| 2022-11-01 | 2 | 20 | 18 | 1 | 10 | 11
| 2022-11-02 | 2 | 20 | 16 | 1 | 10 | 8
| 2022-11-03 | 2 | 20 | 16 | 1 | 10 | 8
| 2022-11-04 | 2 | 20 | 24 | 1 | 10 | 8
| 2022-11-05 | 2 |  | 22 | 1 |  | 8
|  | 2 | 100 | 112 | 1 | 50 | 54
CW45 | 2022-11-07 | 3 | 60 | 27 | 2 | 20 | 14
| 2022-11-08 | 4 | 80 | 40 | 2 | 20 | 9
| 2022-11-09 | 3 | 45 | 42 | 2 | 20 | 9
| 2022-11-10 | 4 | 80 | 64 | 2 | 20 | 24
| 2022-11-11 | 5 | 95 | 88 | 2 | 30 | 30
| 2022-11-12 | 5 |  | 50 | 2 |  | 30
|  | 4 | 360 | 311 | 2 | 110 | 116
CW46 | 2022-11-14 | 5 | 100 | 60 | 2 | 40 | 35
| 2022-11-15 | 5 | 60 | 50 | 2 | 20 | 19
| 2022-11-16 | 5 | 75 | 70 | 2 | 25 | 15
| 2022-11-17 | 5 | 78 | 73 | 2 | 30 | 28
| 2022-11-18 | 5 | 80 | 71 | 2 | 40 | 41
| 2022-11-19 | 4 |  | 20 | 2 |  | 12
|  | 4.8333 | 393 | 344 | 2 | 155 | 150
CW47 | 2022-11-21 | 3 | 80 | 46 | 2 | 30 | 17
| 2022-11-22 | 3 | 60 | 46 | 2 | 40 | 37
| 2022-11-23 | 3 | 60 | 43 | 2 | 40 | 30
| 2022-11-24 | 3 | 60 | 38 | 2 | 40 | 19
| 2022-11-25 | 3 | 60 | 48 | 2 | 40 | 26
| 2022-11-26 | 1 |  | 8 | 2 |  | 28
|  | 2.6667 | 320 | 229 | 2 | 190 | 157
CW48 | 2022-11-28 | 2 | 35 | 33 | 2 | 30 | 27
| 2022-11-29 | 3 | 40 | 38 | 2 | 30 | 30
| 2022-11-30 | 3 | 46 | 46 | 2 | 40 | 38
| 2022-12-01 | 2 | 30 | 30 | 2 | - | -
| 2022-12-02 | 2 | 30 | 26 | 2 | - | -
|  | 2.4 | 181 | 173 | 2 | 100 | 95
CW49 | 2022-12-05 | 2 | 40 | 41 | 2 | 40 | 37
| 2022-12-06 | 2 | 40 | 40 | 2 | 30 | 32
| 2022-12-07 | 2 | 40 | 41 | 2 | 30 | 30
| 2022-12-08 | 2 | 34 | 32 | 2 | 30 | 30
| 2022-12-09 | 1 | 15 | 15 | 2 | 30 | 31
|  | 1.8 | 169 | 169 | 2 | 160 | 160
CW50 | 2022-12-12 | 2 | - | - | 2 | - | -
| 2022-12-13 | 2 | 40 | 40 | 2 | - | -
| 2022-12-14 | 2 | 40 | 34 | 2 | - | -
| 2022-12-15 | 2 | 14 | 13 | 2 | 40 | 36
| 2022-12-16 | 2 | 27 | 28 | 2 | 28 | 20
|  | 2 | 121 | 115 | 2 | 68 | 56
CW51 | 2022-12-19 | 2 | 27 | 27 | 2 | 40 | 41
| 2022-12-20 | 2 | 22 | 23 | 2 | 40 | 40
| 2022-12-21 | 2 | 22 | 21 | 2 | 40 | 31
| 2022-12-22 | 2 | 22 | 21 | 2 | 40 | 54
| 2022-12-23 | 2 | 22 | 23 | 2 | 40 | 30
|  | 2 | 115 | 115 | 2 | 200 | 196
CW52 | 2022-12-26 | 2 | 24 | 25 | 2 | 40 | 35
| 2022-12-27 | 2 | 24 | 24 | 2 | 40 | 45
| 2022-12-28 | 2 | 24 | 24 | 2 | 40 | 40
| 2022-12-29 | 2 | 24 | 20 | 2 | 40 | 40
| 2022-12-30 | 2 | 24 | 24 | 2 | 40 | 30
|  | 2 | 120 | 117 | 2 | 200 | 190
2023-2024
CW01 | 2023-01-02 | 2 | 24 | 24 | 2 | 40 | 42
| 2023-01-03 | 2 | 24 | 24 | 2 | 40 | 39
| 2023-01-04 | 2 | 24 | 24 | 2 | 40 | 38
| 2023-01-05 | 2 | 24 | 29 | 2 | 30 | 30
| 2023-01-06 | 2 | 24 | 27 | 2 | 30 | 30
|  | 2 | 120 | 128 | 2 | 180 | 179
CW02 | 2023-01-09 | 2 | 24 | 22 | 2 | 30 | 30
| 2023-01-10 | 2 | 24 | 24 | 2 | 30 | 31
| 2023-01-11 | 2 | 18 | 18 | 2 | 30 | 30
| 2023-01-12 | 2 | 18 | 18 | 2 | 30 | 30
| 2023-01-13 | 2 | 18 | 20 | 3 | 45 | 46
|  | 2 | 102 | 102 | 2.2 | 165 | 167
CW03 | 2023-01-16 | 2 | 18 | 18 | 1 | 15 | 15
| 2023-01-17 | 2 | 18 | 18 | 1 | 15 | 15
| 2023-01-18 | 2 | 26 | 28 | 1 | 15 | 15
| 2023-01-19 | 2 | 40 | 33 | 1 | 15 | 15
| 2023-01-20 | 2 | 35 | 22 | 1 | 20 | 20
|  | 2 | 137 | 119 | 1 | 80 | 80
CW04 | 2023-01-23 | 1 | 20 | 20 | 2 | 40 | 40
| 2023-01-24 | 1 | 20 | 20 | 2 | 40 | 40
| 2023-01-25 | 1 | 20 | 20 | 2 | 40 | 40
| 2023-01-26 | - | - | - | - | - | -
| 2023-01-27 | 1 | 20 | 20 | 2 | 40 | 40
|  | 1 | 80 | 80 | 2 | 160 | 160
CW05 | 2023-01-30 | 2 | 40 | 40 | 2 | 40 | 40
| 2023-01-31 | 2 | 30 | 30 | 2 | 40 | 40
| 2023-02-01 | 2 | 33 | 33 | 2 | 40 | 40
| 2023-02-02 | 2 | 40 | 40 | 2 | 40 | 40
| 2023-02-03 | 2 | 40 | 40 | 2 | 40 | 40
|  | 2 | 183 | 183 | 2 | 200 | 200
CW06 | 2023-02-06 | 2 | 40 | 40 | 2 | 40 | 40
| 2023-02-07 | 2 | 40 | 40 | 2 | 40 | 40
| 2023-02-08 | - | - | - | 2 | 40 | 42
| 2023-02-09 | - | - | - | 2 | 40 | 41
| 2023-02-10 | - | - | - | 2 | 40 | 40
| 2023-02-11 | - | - | - | 2 | 40 | 40
|  | 2 | 80 | 80 | 2 | 200 | 203
CW07 | 2023-02-13 | - | - | - | 2 | 40 | 35
| 2023-02-14 | - | - | - | 2 | 40 | 29
| 2023-02-15 | 2 | 40 | 38 | 2 | 40 | 38
| 2023-02-16 | 2 | 40 | 40 | 2 | 40 | 45
| 2023-02-17 | 1 | 20 | 20 | 2 | 40 | 21
|  | 1.6667 | 100 | 98 | 2 | 200 | 168